## Sheet1
Project Name
| Project Start: | 2023-03-20
|  |  |  | Winter Quarter | [10 empty] | Spring Quarter
Task |  | Assigned To | Progress (%) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | F | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | F
Phase 1 : Team Organization
Task 1.1 : | Organize team structure
Task 1.2 : | Setup filesystem
Task 1.3 : | Start documentation
Phase 2 : Early Concepts
Task 2.1 : | Design ideas for the outershell of Dave
Task 2.2 : | Outershell proof of concepts
Task 2.3 : | On-site testing
Task 2.4 : | Electronic selections
Task 2.5 : | Design ideas for system
Task 2.7 : | Basic CAD drawings of designs
Task 2.6 : | Process the data of proof of concept Dave
Task 2.8 : | Design matrix and selection for system components
Task 2.9 : | Electrical schematics
Task 2.10 : | Heat distribution concepts
Task 2.11 : | Finalize system concept for prototyping phase
Phase 3 : Prototyping
Task 3.1 : | Preliminary simulation of Dave's movements and sensors
Task 3.2 : | CAD of prototype chassis/ drive train
Task 3.3 : | Theoritical subsystem analysis
Task 3.4 : | Finalization simulation
Task 3.5 : | Finalize subsystem components
Task 3.6 : | CAD cable management for finalized system concept
Task 3.7 : | Purchase electronic and mechanical components for subsystems
Task 3.8 : | Manufacture subsystems
Task 3.9 : | Analysis of power distribution of system
Task 3.10 : | Battery selection
Task 3.11 : | Build chassis
Task 3.12 : | Analysis of drivetrain
Task 3.13 : | Software for controlling Dave's movements
Task 3.14 : | Mechanical safety verification across system
Task 3.15 : | Electrical safety verification across system
Task 3.16 : | Software on user interface
Task 3.17 : | Interface electronic components with appropriate subsystems
Task 3.18 : | Finalize Dave Securement Candidate
Task 3.19 : | Dave Securement Site Analysis
Task 3.20 : | Manufacturing of Dave Securement Site
Task 3.21 : | Finalize and Build Electronics in Box
Task 3.22 : | Finalize Battery
Task 3.23 : | Manufacture Battery Securement
Task 3.24 : | Finalize and Attach All Mechanical Subsystems
Task 3.25 : | Build Chassis
Task 3.26 : | Integrate electronic components with chassis sites
Task 3.27 : | Finalizing system changes
Phase 4 : Verification
Task 4.1 : | Verify and validate function requirement
Task 4.2 : | Verify and validate performance requirement
Task 4.3 : | Verify and validate operational and user requirement
Task 4.4 : | Verify and validate enviromental requirement
Task 4.5 : | Verify and validate physical requirement
Task 4.6 : | Verify and validate safety requirement
Phase 5 : Finalization
Task 5.1 : | Finish mechanical system
Task 5.2 : | Finish electrical
Task 5.3 : | Finish software
Task 5.4 : | Finalize verification and validation documentation
Task 5.5 : | Finish documentation
Task 5.6 : | Present final product